## Project schedule
[9 empty] | Project Start Date | [7 empty] | 2025-05-27
| HostelHub | [7 empty] | Current Week | [7 empty] | 1
[9 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14
| TASK | ASSIGNED TO | PROGRESS | START | END | Actual Start | Actual End | time axis 2025-05-26 to 2025-07-20
 | time axis 2025-05-26 to 2025-07-20
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Planning and Ideation
| Define Problem Statement | All Team | 100% | 2025-05-27 | 2025-05-28 | 2025-05-27 | 2025-05-28 | 2
| UI Wireframing | Akanksha Kumbhar and Balaji More | 100% | 2025-05-28 | 2025-06-01 | 2025-05-28 | 2025-01-06 | 5
| ERD chart and Mind Maps | Akansha Kumbhar | 100% | 2025-05-28 | 2025-06-01 | 2025-05-28 | 2025-06-01 | 5
| Gantt Chart | Balaji More | 100% | 2025-05-28 | 2025-06-01 | 2025-05-28 | 2025-06-01 | 5
| RACI Chart | Vaibhav Jadhav | 100% | 2025-05-29 | 2025-06-02 | 2025-05-29 | 2025-06-02
| Project Charter | Tejas Gophane | 100% | 2025-05-29 | 2025-06-02 | 2025-05-29 | 2025-06-02 | 5
Design and Prototyping
| Create detailed wireframe | Akanksha Kumbhar | 80% | 2025-06-02 | 2025-06-04 | 2025-06-02 | 2025-06-04 | 3
| Finalize databara ERD | Vaibhav Jadhav | 100% | 2025-06-02 | 2025-06-04 | 2025-06-02 | 2025-06-04 | 3
| Finalize UI/UX designer | Tejas Gophane | 80% | 2025-06-02 | 2025-06-04 | 2025-06-02 | 2025-06-04 | 3
| Create APl-endpoint plan | Balaji More | 95% | 2025-06-02 | 2025-06-05 | 2025-06-02 | 2025-06-05 | 4
Implementation
| Database Creation & Management | Balaji More | 100% | 2025-06-06 | 2025-06-09 | 2025-06-06 | 2025-06-09 | 4
| Frontend Development | Akanksha Kumbhar | 80% | 2025-06-08 | 2025-06-13 | 2025-06-08
| Backend API development | Tejas Gophane | 95% | 2025-06-08 | 2025-06-13 | 2025-06-08 |  | 6
| Integration and Testing | Vaibhav Jadhav |  | 2025-06-13 | 2025-06-15 |  |  | 3
Testing, Deployment and Review
| Testing & Bug Fixing | Akanksha Kumbhar |  | 2025-06-15 | 2025-06-17 |  |  | 3
| Final Deployment | Tejas Gophane |  | 2025-06-17 | 2025-06-18 |  |  | 2
| Final demo and Presentation | Balaji More |  | 2025-06-18 | 2025-06-19 |  |  | 2
| Project Documentation | Vaibhav Jadhav |  | 2025-06-19 | 2025-06-20 |  |  | 2
Insert new rows ABOVE this one